## Field Mapping
# | Manual Field | Category | Map Status | TowerOS Module | Table / Entity | System Field | How to Get Value in System | Gap / Action
1 | TCO SITE ID | Site ID | Mapped | Rollout | rollout_programs | tco_site_id | Auto-generated on rollout create; shown in rollout detail & export
2 | MNO Anchor Site ID | Site ID | Missing |  |  |  | Not stored today | Add mno_anchor_site_id on rollout or site external refs
3 | MNO Anchor | Site ID | Mapped | Rollout | rollout_programs | mno | Values: globe, smart, dito | Map display names to enum
4 | Globe Project Batch Tagging | Site ID | Partial | Rollout | rollout_programs | parent_rollout_id + search_ring_name | Batch parent (status=batch) groups sites; child rollouts inherit batch | Add explicit batch_tag / globe_batch_ref if needed
5 | Project Type | Site ID | Mapped | Rollout | rollout_programs | project_type | bts, rtb, colocation/colo
6 | ALLIANCE TAGGING | Site ID | Missing |  |  |  | Not in schema | Add custom tag field or tenant metadata on rollout
7 | Region | Geography | Mapped | Rollout | rollout_programs | region | Set on rollout create/update
8 | Area | Geography | Missing |  |  |  | Only region + territory exist | Add area or map to territory hierarchy
9 | Territory | Geography | Mapped | Rollout | rollout_programs | territory | Set on rollout create/update
10 | Search Ring Name | Geography | Mapped | Rollout | rollout_programs | search_ring_name | Direct field
11 | Latitude (Actual) | Geography | Partial | Sites / SAQ | sites or site_candidates | latitude | Canonical coords on linked site; hunting coords on selected candidate | Ensure candidate→site promotion copies coords
12 | Longitude (Actual) | Geography | Partial | Sites / SAQ | sites or site_candidates | longitude | Same as latitude | Same
13 | Full Address | Geography | Missing |  |  |  | sites has no address | Add full_address (or structured address) on sites
14 | Solution | Technical | Missing |  |  |  | Not distinct from project_type | Add solution if different from project type
15 | Tower Height | Technical | Partial | TowerOne | towers | height_m | Via site → tower record | Link rollout site to tower
16 | Tower Type | Technical | Partial | TowerOne / Sites | towers.tower_type or sites.type | tower_type / type | Tower module or site type (macro, rooftop, etc.) | Clarify which manual value maps where
17 | Wind Speed | Technical | Missing |  |  |  | Not in schema | Add on site/tower engineering profile
18 | MNO 2 | Coloc | Different Model | Rollout | child rollout_programs | mno | Model as colocation child rollout, not column | Build coloc registry UI or import as child rows
19 | Coloc 2 Site ID | Coloc | Different Model | Rollout | child rollout | tco_site_id or endorsement_ref | Per-tenant coloc rollout | Same
20 | Coloc 2 Site Name | Coloc | Different Model | Sites | sites | name | Via linked site on child rollout | Same
21 | RFTI Date (Coloc 2) | Coloc | Different Model | Rollout | child rollout | actual_rfi_date | Record RFI on coloc rollout | Same
22 | SL Remarks (Coloc 2) | Coloc | Missing |  |  |  | No remarks field for site license | Add site_license_remarks on rollout
23 | MNO 3 | Coloc | Different Model | Rollout | 2nd child rollout | mno | Same pattern as Coloc 2 | Same
24 | Coloc 3 Site ID | Coloc | Different Model | Rollout | 2nd child | tco_site_id | Same | Same
25 | Coloc 3 Site Name | Coloc | Different Model | Sites | sites | name | Same | Same
26 | RFTI Date (Coloc 3) | Coloc | Different Model | Rollout | 2nd child | actual_rfi_date | Same | Same
27 | SL Remarks (3) | Coloc | Missing |  |  |  | Same as Coloc 2 remarks | Add site_license_remarks
28 | MOC Secured | Permitting | Partial | Rollout Playbook | milestone moc_securing / phase moc_col | actual_end_date | Derived from timeline, not standalone column | Optional: add explicit moc_secured_date
29 | Brgy. Clearance Applied | Permitting | Missing |  |  |  | Not granular | Add permit tracker sub-entity or custom phase
30 | Brgy Clearance Secured | Permitting | Missing |  |  |  | LGU clearance exists as optional custom phase only | Add brgy_clearance permit record
31 | Locational Clearance Applied | Permitting | Partial | Rollout Playbook | milestone locational_clearance | start date | Milestone cycle; no separate Applied vs Secured | Split applied/secured if required
32 | Locational Clearance Secured | Permitting | Partial | Rollout Playbook | phase permitting / milestone locational_clearance | actual_end_date | Use phase actual end or bulk phase dates API | Same
33 | Excavation Permit Applied | Permitting | Missing |  |  |  | Not in playbook milestones | Add permit sub-tracker
34 | Excavation Permit Secured | Permitting | Missing |  |  |  | Same | Same
35 | Building Permit Applied | Permitting | Partial | Rollout Playbook | milestone building_permit | start date | Milestone in cycle | No applied/secured split
36 | Building Permit Secured | Permitting | Partial | Rollout Playbook | phase / milestone building_permit | actual_end_date | Phase actual dates | Same
37 | Occupancy Permit Applied | Permitting | Missing |  |  |  | Not in playbook | Add permit tracker
38 | Occupancy Permit Secured | Permitting | Missing |  |  |  | Same | Same
39 | CFEI Applied | Permitting | Missing |  |  |  | Not in playbook | Add permit tracker
40 | CFEI Secured | Permitting | Missing |  |  |  | Same | Same
41 | Date Endorsed by Globe | Milestones | Mapped | Rollout | rollout_programs | endorsement_date | Direct field (+ endorsement_ref)
42 | TSSR Submitted | Milestones | Partial | Rollout Playbook | phase tssr_creation / milestone tssr_mno_approval | actual_start_date or actual_end_date | From timeline phase dates | Add explicit tssr_submitted_date if needed
43 | TSSR Approved | Milestones | Mapped | Rollout | rollout_programs | tssr_approved_date | Day-1 trigger for BTS; POST .../tssr-approved
44 | Risk Build Declared Date | Milestones | Partial | Rollout Playbook | phase permitting | actual_end_date (Risk Build gate) | Permitting phase gate, not dedicated date column | Add risk_build_declared_date for Excel parity
45 | CW Start Date | Milestones | Partial | Rollout Playbook | phase construction / milestone construction | actual_start_date | Timeline + CME reports
46 | CW Completed Date | Milestones | Partial | Rollout Playbook | milestone construction | actual_end_date | Milestone cycle segment end
47 | Energization Tempo Date | Milestones | Missing |  |  |  | Energization merged into construction phase in timeline | Add energization_tempo_date or split energization milestone
48 | Energization (Permanent) | Milestones | Partial | Rollout Playbook | milestone energization | actual_end_date | Fine-grained milestone in cycle | Tempo vs permanent not split
49 | RFTI Docs Submitted | Milestones | Partial | Rollout Playbook | milestone rfti_submission | milestone dates | Milestone cycle
50 | RFTI Docs Signed (Tempo) | Milestones | Missing |  |  |  | No tempo vs permanent RFTI split | Add rfti_signed_tempo_date
51 | RFT Docs Signed (Permanent) | Milestones | Mapped | Rollout | rollout_programs | actual_rfi_date | POST .../rfi-recorded (RFI in system = RFT in manual)
52 | SL Submitted | Milestones | Partial | Rollout Playbook | milestone site_license | start / target dates | Milestone cycle
53 | SL Signed | Milestones | Mapped | Rollout | rollout_programs | site_license_executed_date | Day-1 for colocation; direct field

## Gap Summary
Priority | Gap Area | Manual Fields Affected | Recommended Action | Suggested Module
P1 | MNO external site reference | MNO Anchor Site ID | Add mno_anchor_site_id on rollout_programs or site external refs table | Rollout / Sites
P1 | Site address | Full Address | Add full_address (or structured address fields) on sites | Sites
P1 | Geography hierarchy | Area | Add area field or formal region → area → territory hierarchy | Rollout
P1 | Permit tracker | Brgy, Excavation, Occupancy, CFEI (Applied/Secured pairs) | New rollout_permits table: permit_type, applied_date, secured_date, notes | Rollout
P1 | Reporting tags | Globe Project Batch Tagging, ALLIANCE TAGGING | Add batch_tag and alliance_tag on rollout_programs | Rollout
P1 | Coloc tenant registry | MNO 2/3, Coloc Site ID/Name, RFTI, SL Remarks | Child rollouts + optional rollout_coloc_tenants summary table with remarks | Rollout
P2 | Split milestone dates | TSSR Submitted, Risk Build, Energization Tempo, RFTI Signed Tempo | Add dedicated date columns or extend milestone cycle with sub-checkpoints | Rollout Playbook
P2 | Permit applied vs secured | Locational, Building (partial today) | Extend permit tracker with applied_date + secured_date per type | Rollout
P3 | Engineering profile | Solution, Wind Speed | Add on site/tower engineering metadata | TowerOne / Sites
| Architecture note | All coloc columns | Manual = flat columns; TowerOS = child rollouts via parent_rollout_id | Rollout
| Terminology | RFTI / RFT | System uses actual_rfi_date (RFI = Ready for Integration) | Rollout

## Phase Reference
Manual Date Column | Primary System Target | Table / Phase Key | Field | Import Method
Date Endorsed by Globe | Rollout header | rollout_programs | endorsement_date | PATCH rollout
TSSR Submitted | Timeline phase | tssr_creation | actual_end_date | Bulk phase dates API
TSSR Approved | Rollout header | rollout_programs | tssr_approved_date | POST .../tssr-approved
MOC Secured | Milestone / phase | moc_securing / moc_col | actual_end_date | Bulk phase dates API
Locational Clearance Applied | Milestone | locational_clearance | start (phase actual_start) | Bulk phase dates API
Locational Clearance Secured | Milestone | locational_clearance | actual_end_date | Bulk phase dates API
Building Permit Applied | Milestone | building_permit | start | Bulk phase dates API
Building Permit Secured | Milestone | building_permit | actual_end_date | Bulk phase dates API
Risk Build Declared Date | Timeline phase | permitting | actual_end_date | Bulk phase dates API or new field
CW Start Date | Timeline / milestone | construction | actual_start_date | Bulk phase dates API
CW Completed Date | Milestone | construction | actual_end_date | Bulk phase dates API
Energization Tempo Date | Not available |  |  | Add new field
Energization (Permanent) | Milestone | energization | actual_end_date | Bulk phase dates API
RFTI Docs Submitted | Milestone | rfti_submission | target/actual dates | Bulk phase dates API
RFTI Docs Signed (Tempo) | Not available |  |  | Add new field
RFT Docs Signed (Permanent) | Rollout header | rollout_programs | actual_rfi_date | POST .../rfi-recorded
SL Submitted | Milestone | site_license | start dates | Bulk phase dates API
SL Signed | Rollout header | rollout_programs | site_license_executed_date | PATCH rollout
RFTI Date (Coloc 2/3) | Child rollout | rollout_programs (child) | actual_rfi_date | Create child rollout + record RFI

## Milestone Cycle
phase_key | label | target_working_days (BTS) | Maps to Manual Tracker
endorsement_to_hunting | Endorsement → Site Hunting Start | 1 | Date Endorsed by Globe (indirect)
site_hunting | Site Hunting (3 candidates) | 7
pre_assessment | Pre-assessment Approval | 2
tssr_creation | TSSR Creation + Internal Review | 2 | TSSR Submitted (partial)
tssr_mno_approval | TSSR Submission → MNO Approval | 9 | TSSR Submitted → TSSR Approved
moc_securing | MOC Securing | 8 | MOC Secured
col_social | COL + Social Acceptability | 8
pre_construction | Pre-Construction Works | 7
ddd | DDD | 5
boq | BOQ | 2
permit_prep | Permit Requirement Prep | 1
locational_clearance | Locational/Zoning Clearance | 14 | Locational Clearance Applied/Secured
building_permit | Building Permit Application | 14 | Building Permit Applied/Secured
skom | SKOM / Mobilization | 1
construction | Construction Phase | 44 | CW Start / CW Completed
energization | Energization | 15 | Energization Tempo / Permanent
rfti_submission | RFTI Submission | 7 | RFTI Docs Submitted
site_license | Site License | 7 | SL Submitted / SL Signed (partial)
billing | Billing | 2

## System Only Fields
System Field | Module | Table | Description | In Manual Tracker?
rollout_ref | Rollout | rollout_programs | Unique rollout reference | No
endorsement_ref | Rollout | rollout_programs | MNO endorsement reference | No
sla_working_days | Rollout | rollout_programs | SLA budget (working days) | No
target_rfi_working_date | Rollout | rollout_programs | Computed target RFI date | No
sla_variance_working_days | Rollout | rollout_programs | SLA variance | No
doa_execution_date | Rollout | rollout_programs | RTB Day-1 trigger | No
saq_owner_id / cme_pm_id / pmo_owner_id | Rollout | rollout_programs | Assigned owners | No
project_id | Rollout | rollout_programs | Link to QMS project | No
site_code | Sites | sites | Canonical site code | No
gate_status / gate_label | Rollout Playbook | rollout_timeline_phases | Per-phase gate tracking | No
site_candidates | SAQ | site_candidates | ≥3 hunting candidates with lease package | No
cme_daily_reports | CME | cme_daily_reports | Daily construction progress | No
site_profitability_records | Finance | site_profitability_records | VO, LD, profitability status | No
rollout_gate_approval_requests | Governance | rollout_gate_approval_requests | Gate approval workflow | No

## Scorecard
Map Status | Count | Description
Mapped | 12 | Direct 1:1 field exists
Partial | 18 | Exists but different shape (phases, related entity, merged fields)
Different Model | 8 | Coloc columns → child rollouts
Missing | 15 | No system field today
Total manual fields | 53 | From manual site tracker screenshot
Generated | 2026-07-06 08:06:04 UTC | TowerOS Project One field mapping
Source | Manual site tracker (Excel) vs Project One + Rollout module